Table of Contents

# FUNDING & FINANCIAL STRATEGY

## Nigeria’s National Genomics & Digital Health Infrastructure Program

Program Scope: $50-150M over 5-10 years
Sustainability Target: 60-70% self-funded by Year 5
Core Innovation: Commercial revenue from Day 1 (avoiding H3Africa’s grant-dependency failure)

# EXECUTIVE SUMMARY

## The Challenge

H3Africa spent $180M over 10 years building world-class genomics capacity across Africa. When grants ended in 2022, African governments couldn’t sustain the infrastructure. Research centers closed. Equipment sat idle. Scientific excellence without financial sustainability equals failure.

## Our Three-Phase Model

| Phase | Timeline | Grant % | Pharma % | Platform % | Equity/Other % |
| --- | --- | --- | --- | --- | --- |
| 1. Launch | Year 1-2 | 60% | 10% | 10% | 20% |
| 2. Hybrid | Year 3-5 | 35% | 30% | 20% | 15% |
| 3. Sustainable | Year 6-10 | 10% | 25% | 50% | 15% |

## Total Funding Target: $88-159M (5 Years)

| Source | Year 1-2 | Year 3-5 | 5-Year Total | % |
| --- | --- | --- | --- | --- |
| International Donors | $10-18M | $15-25M | $25-43M | 25-28% |
| Pharmaceutical Partnerships | $8-15M | $12-20M | $20-35M | 20-23% |
| Platform Revenue (MeddyPal) | $3-6M | $10-20M | $13-26M | 13-17% |
| Equity Investment (NEW) | $2-5M | $8-15M | $10-20M | 10-12% |
| Research-Funded Testing (NEW) | $1-3M | $4-12M | $5-15M | 5-10% |
| Genomic Services Revenue | $0.5-1M | $5-10M | $5.5-11M | 5-7% |
| Government (Cash + In-Kind) | $4-7M | $7-13M | $11-20M | 11-13% |
| Equipment/Cloud In-Kind | $4-7M | $2-4M | $6-11M | 6-7% |
| TOTAL | $32.5-62M | $63-129M | $95.5-191M | 100% |

## Critical Success Factors

- MeddyPal generates revenue from Month 3 (not Year 3)

- Pharmaceutical partnerships locked by Year 2 (before grant fatigue)

- Research funding subsidizes “free” genomic testing (user acquisition)

- Equity investment unlocked via SPV structure (Year 2+)

- Government contribution increases gradually (builds political ownership)

## The Core Principle

Every dollar of grant funding must either: - Build revenue-generating capacity (platform, genomics services) - Reduce future costs (equipment donations, training) - Lock in sustainable partnerships (pharma, government)

# SECTION 1: PARTNERSHIP STRUCTURE OPTIONS

## 1.1 Two Structural Paths

| Factor | Direct Partnership (MOU) | SPV Model |
| --- | --- | --- |
| Setup Time | 4-8 weeks | 8-16 weeks |
| Setup Cost | $10-20K legal | $50-100K legal + incorporation |
| Best For | Pilot phase (Year 1-2) | Scale phase (Year 2+) |
| Equity Investment | ❌ Cannot accept | ✅ Can accept IFC, NSIA, pharma |
| Adding Partners | Complex (new agreements) | Simple (add shareholder) |
| Grant Recipient Clarity | Moderate (which entity?) | High (single entity) |
| Asset Protection | Moderate | Strong (separate legal entity) |
| Pharma Partner Comfort | Moderate | High (clear contracting party) |
| Exit Strategy | Difficult (unwind contracts) | Clean (sell shares) |
| International Arbitration | Requires specific clauses | Standard for Nigerian companies |
| Board Governance | Informal steering committee | Formal board of directors |

## 1.2 Direct Partnership Model (Current MOU)

Federal Government of Nigeria
              │
              ▼
    NABDA (Government Partner)
              │
              │ ←──── MOU ────→ Basani Digital Innovations (Private Partner)
              │                              │
              │                              │
              ▼                              ▼
    Government Assets:               Forric Technologies (IP Owner)
    - Lab space                            │
    - Equipment (needs assessment)         │
    - Regulatory access                    ▼
    - Staff (in-kind)                 MeddyPal Platform
                                      AI/ML Models
                                      Commercial Operations

Pros: - Speed to start (4-8 weeks) - Lower setup cost ($10-20K) - Maximum flexibility for pivots - Basani retains full control of operations - Suitable for pilot/validation phase

Cons: - Cannot accept equity investment - Complex to add Syndicate Bio as equal partner - Weaker asset protection - Donor concerns for large grants ($10M+) - Difficult exit if partnership fails

## 1.3 SPV Model (For Scale Phase)

SHAREHOLDERS
    ┌─────────────────────┬────────────────────┬─────────────────────┐
    │                     │                    │                     │
    ▼                     ▼                    ▼                     ▼
NABDA (25-33%)     Basani (35-40%)    Syndicate Bio (25-35%)   IFC/NSIA (15-20%)
    │                     │                    │                     │
    └─────────────────────┴────────────────────┴─────────────────────┘
                                    │
                                    ▼
                Nigerian Genomics Initiative Ltd
                (Special Purpose Vehicle - SPV)
                                    │
              ┌─────────────────────┼─────────────────────┐
              │                     │                     │
              ▼                     ▼                     ▼
        Biobank Operations    Platform Operations   Research Programs
        (Genomic Services)    (MeddyPal License)    (Grant Recipient)

Structure: Nigerian Limited Liability Company (Ltd/Gte or Ltd by Shares)

Pros: - Equity investment eligible (IFC, NSIA, pharma strategic) - Easy to add/remove partners (buy/sell shares) - Clean governance (formal board, clear voting) - Donors prefer single entity for large grants - Asset protection (SPV owns assets, not partners) - Standard pharma contracting structure - Clean exit path (sell shares) - Can include international arbitration clauses

Cons: - Setup complexity (8-16 weeks, $50-100K) - Governance overhead (board meetings, minutes, filings) - Potential board deadlock if not structured carefully - Government scrutiny (NABDA as shareholder requires approvals) - Less flexibility than MOU - Tax complications (corporate tax, transfer pricing)

## 1.4 Recommendation: Phased Approach

| Phase | Timeline | Structure | Rationale |
| --- | --- | --- | --- |
| Phase 1 | Year 1-2 | Direct Partnership (MOU) | Speed, low cost, prove concept |
| Phase 2 | Year 2+ | Transition to SPV | When scale triggers met |

Transition Triggers (any one triggers SPV formation): 1. First $5M+ grant secured (donor preference for single entity) 2. Syndicate Bio partnership confirmed (need shareholding structure) 3. IFC/NSIA equity investment opportunity (requires equity-eligible entity) 4. Total program funding exceeds $20M (complexity warrants formal structure)

Preparation During Phase 1: - Draft Shareholders’ Agreement in principle - Reserve company name with CAC - Agree shareholding percentages in principle - Include SPV transition clause in MOU

## 1.5 Shareholding Scenarios (If SPV Formed)

### Scenario A: Two-Party (NABDA + Basani Only)

| Shareholder | Equity | Board Seats | Rationale |
| --- | --- | --- | --- |
| NABDA | 33% | 2 | Government legitimacy, regulatory access |
| Basani | 67% | 3 | Operational control, IP contribution |

### Scenario B: Three-Party (With Syndicate Bio)

| Shareholder | Equity | Board Seats | Contribution |
| --- | --- | --- | --- |
| NABDA | 25% | 2 | Government partnership, regulatory |
| Basani | 40% | 2 | Platform, commercial operations |
| Syndicate Bio | 35% | 2 | Genomics expertise, lab capacity |

### Scenario C: Four-Party (With Equity Investor)

| Shareholder | Equity | Board Seats | Contribution |
| --- | --- | --- | --- |
| NABDA | 20% | 1 | Government partnership |
| Basani | 35% | 2 | Platform, operations |
| Syndicate Bio | 25% | 1 | Genomics, pharma access |
| IFC/NSIA | 20% | 1 | Capital, credibility |

Key Governance Provisions: - Reserved matters requiring supermajority (IP licensing, major contracts, M&A) - Anti-deadlock mechanisms (casting vote, mediation, shotgun clause) - Tag-along/drag-along rights for exit - Pre-emptive rights on new share issuance - NABDA veto on matters affecting government interests

# SECTION 2: INTERNATIONAL DONOR FUNDING ($25-43M)

## 2.1 Tier 1: Large Multilateral Funds ($15-30M)

### A. World Bank Pandemic Fund: $10-25M (HIGHEST PRIORITY)

Why This is #1: - Nigeria explicitly listed as eligible for March 2026 round - Single-country proposals can access $25M - 3 priority investment areas directly support genomics - Applications accepted over 1-year window (flexibility)

Application Structure:

| Role | Entity | Responsibility |
| --- | --- | --- |
| Lead Applicant | Federal Ministry of Health | REQUIRED by Pandemic Fund rules |
| Implementation Partner | NABDA-Basani | Technical execution |
| Approved Implementing Entity | World Bank | Fiduciary management |

Proposal Framework (Due March 2026):

| Component | Budget | Focus |
| --- | --- | --- |
| Genomic Surveillance Infrastructure | $12M | NGS equipment, biobank, NCDC integration, AI dashboard |
| Laboratory Workforce Capacity | $8M | 500+ professionals trained, national training center, 10 PhDs + 30 MSc |
| Digital Health Integration | $5M | MeddyPal deployment, federated data architecture, mobile apps |

Immediate Actions: 1. Week 1: Contact Ministry of Health (coordinate through Minister of Science & Tech) 2. Week 2: Engage World Bank Nigeria office (Douglas Ogbonnaya, Health Specialist) 3. Week 3: Secure formal MOH endorsement letter 4. Month 2: Draft concept note

Success Probability: 70-80% (Nigeria explicitly targeted, strong precedent)

Critical Dependencies: - ✓ Ministry of Health must lead (not NABDA directly) - ✓ Requires demonstrating government co-financing commitment - ✓ Must show integration with existing health systems - ✓ Environmental and social safeguards compliance

### B. World Bank IDA/IBRD Portfolio: $10-20M

Active Opportunities:

| Program | Amount | Focus | Strategy |
| --- | --- | --- | --- |
| Health Security Program (HeSP) Phase II | $250M (approved Oct 2025) | Pandemic preparedness | Request $10M genomics component |
| HOPE-PHC Digital Health | $15M (approved) | Federated digital health | Request $5M MeddyPal integration |
| MAMA Fund | Part of HOPE-PHC | Maternal/child health | Request $5-8M genomics-enhanced maternal care |

Strategy: Don’t apply standalone. Position as component within existing programs. Leverage NSIA’s World Bank relationship. Emphasize maternal health (MAMA Fund sweet spot).

Timeline: - Month 1-2: Meetings with World Bank team - Month 3-4: Concept notes for program components - Month 6-9: Formal proposals if concepts approved - Month 12-18: Funding approval and disbursement

### C. African Development Bank: $10-20M

Why AfDB: - Nigeria portfolio: $5.1 billion across 52 projects - Recently approved Sokoto Health Infrastructure ($46M, July 2025) - 2025-2028 pipeline: $2.4B sovereign + $500M private sector - Private sector window perfect for Basani

Funding Vehicles:

| Vehicle | Terms | Maximum | Best For |
| --- | --- | --- | --- |
| Nigeria Trust Fund | 4% interest, 25 years, 5-year grace | $10M | Sovereign guarantee available |
| Private Sector Window | Market rates | $20M | Basani direct application |
| Africa Investment Forum | Varies | $50M+ | Large-scale infrastructure |

Entry Point: Abdul Kamara, Director General, Nigeria Country Office

Pitch: “National genomics infrastructure aligned with AfDB health strategy”

Timeline: - Month 2-3: Initial meeting with DG - Month 4-6: Concept note submission - Month 9-12: Board approval if concept approved

## 2.2 Tier 2: Foundations ($8-15M)

### A. Gates Foundation: $5-15M (70% Probability)

Entry Points: - Grand Challenges Phase 1: $100K exploratory → Phase 2: $1-3M - Direct application: $5-15M for sickle cell genomics - Co-funding with Novartis on SCD research

Our Pitch: - Nigeria = highest SCD burden globally (150K births/year) - MeddyPal provides longitudinal outcomes data (unique) - Government partnership = pathway to scale

Contact: - Trevor Mundel, President, Global Health Division - Emeka Okafor, Nigeria Country Office

Application Strategy: 1. Month 2: Submit Grand Challenges Phase 1 ($100K for SCD pilot) 2. Month 8: If successful, submit Phase 2 ($2-5M) 3. Month 12: If Phase 1 successful, submit direct application ($5-10M)

### B. Wellcome Trust: $5-10M (60% Probability)

Relevant Programs:

| Program | Amount | Focus | Deadline |
| --- | --- | --- | --- |
| DELTAS Africa III | £5-8M | Research capacity | Expected Q2-Q3 2025 |
| Discovery Awards | £150K-£300K | Novel genomics | Rolling |
| Climate & Health | £1-2M | Environmental genomics | Annual |

Strategy: Position as DELTAS consortium with University of Lagos and Redeemer’s ACEGID

Contact: Michael Turner, Africa Program Director

### C. Mastercard Foundation: $3-5M (40% Probability)

Focus: Young Africa Works (digital skills, employment)

Our Angle: Genomics/bioinformatics training creates high-value jobs

Application Route: Through Scholars Program or Young Africa Works partnership

## 2.3 Tier 3: Research Programs ($8-15M)

### A. EDCTP3: €8-15M (55% Probability)

European & Developing Countries Clinical Trials Partnership

Relevant Calls:

| Call | Amount | Focus | Deadline |
| --- | --- | --- | --- |
| Clinical Trials Capacity | €8-12M | Infrastructure for trials | March 2025 Stage 1 |
| Digital Health Integration | €5-8M | eHealth + diagnostics | Q3 2025 |
| One Health | €3-5M | Zoonotic diseases | Q4 2025 |

Application Requirements: - Lead: African research institution (NABDA qualifies) - European partner required (potential: Sanger Institute, Karolinska) - 2-stage application (Stage 1: 5-page concept; Stage 2: full proposal)

Timeline: - March 15, 2025: Stage 1 pre-proposal due - September 2025: Stage 2 full proposal (if invited) - January 2026: Funding decision

### B. NIH Fogarty International Center: $2-5M (50% Probability)

Programs:

| Program | Amount | Focus |
| --- | --- | --- |
| D43 Training Grant | $250K/year x 5 | Research training |
| H3Africa Administrative Supplement | $500K-1M | Existing H3Africa enhancement |
| Emerging Global Leader Award | $100K/year x 5 | Early-career researchers |

Strategy: Partner with US institution (potential: Duke, Harvard School of Public Health)

### C. JICA SATREPS: ¥300-500M (~$2-2.8M) (40% Probability)

Science and Technology Research Partnership for Sustainable Development

Requirements: - Japanese research partner (potential: Nagasaki University - existing Nigeria ties) - 3-5 year projects - Annual call (November)

Our Pitch: Japan-Nigeria genomics partnership for infectious disease surveillance

## 2.4 Tier 4: Bilateral Development Agencies ($3-8M)

### A. USAID: $3-5M (50% Probability)

Entry Points:

| Program | Amount | Focus |
| --- | --- | --- |
| Digital Invest | $1-5M | Digital health innovation |
| Global Health Security Agenda | $2-5M | Disease surveillance |
| PEPFAR Innovation | $500K-2M | HIV genomics |

Contact: USAID Nigeria Health Office

### B. UK FCDO: $2-4M (40% Probability)

Programs: - Fleming Fund: £3-5M for AMR genomics - Global Health Research Programme: £1-2M

Strategy: Apply through Fleming Fund via Mott MacDonald (implementing partner)

### C. German GIZ: $2-4M (40% Probability)

Programs: - African-German Partnership for Health: €2-3M - BACKUP Health: €500K-1M

## 2.5 International Donor Summary & Timeline

### 90-Day Priority Applications

| Funder | Target Amount | Deadline | Lead | Action |
| --- | --- | --- | --- | --- |
| EDCTP3 Stage 1 | €8-15M | March 15, 2025 | NABDA | SUBMIT PRE-PROPOSAL |
| Gates Grand Challenges | $100K-500K | Rolling | Basani | SUBMIT MONTH 2 |
| Pandemic Fund Concept | $15-25M | March 2026 | MOH | DRAFT CONCEPT |
| AWS Cloud Credits | $3-5M | Rolling | Basani | SUBMIT MONTH 1 |
| Fleming Fund EOI | £3-4M | Rolling | NCDC+NABDA | EOI MONTH 2 |

### 12-Month Expected Outcomes

| Timeline | Milestone | Cumulative Secured |
| --- | --- | --- |
| Month 3 | AWS credits approved, 3-5 applications submitted | $3-5M |
| Month 6 | Fleming Fund approved, EDCTP Stage 2 invited | $6-10M |
| Month 9 | AfDB approved, EDCTP Stage 2 submitted | $15-25M |
| Month 12 | EDCTP approved, TETFund approved | $25-40M |

# SECTION 3: EQUITY & INVESTMENT FUNDING ($10-20M) ⭐ NEW

## 3.1 Why Equity Matters

Grants vs. Equity: - Grants fund activities → end when activities complete - Equity funds company building → permanent capital for growth - Equity investors aligned with long-term success - Equity unlocks additional debt financing

Requirement: SPV structure required for equity investment

## 3.2 Development Finance Institutions (DFIs)

### A. IFC (World Bank Group): $10-50M (60% Probability)

Investment Thesis for IFC: - Development impact: Nigeria’s 220M population - Financial sustainability: MeddyPal revenue model proven - Private sector leadership: Basani execution capability - Government partnership: NABDA legitimacy - Scalable model: Replicable across Africa

Typical IFC Terms:

| Element | Typical Range |
| --- | --- |
| Investment Size | $15-25M |
| Equity Stake | 20-30% |
| Board Seats | 1-2 directors |
| Exit Horizon | 7-10 years |
| IRR Expectation | 15-20% |

Application Process: 1. Initial screening (2-3 months) 2. Appraisal and due diligence (4-6 months) 3. Board approval (2-3 months) 4. Legal and disbursement (2-3 months) - Total: 12-18 months from first contact

Entry Point: IFC Nigeria Office, Health & Education Team

### B. Other DFIs

| Institution | Amount | Probability | Focus |
| --- | --- | --- | --- |
| AfDB Private Sector | $10-30M | 50% | African health infrastructure |
| CDC (UK DFI) | $10-25M | 50% | Impact-first equity |
| DFC (US DFI) | $10-50M | 40% | Strategic sectors |

## 3.3 Nigerian Sovereign Funds (HIGHEST DOMESTIC PRIORITY)

### A. NSIA (Nigeria Sovereign Investment Authority): $10-50M (70% Probability)

Why NSIA is Critical: - Mandate: Nigerian infrastructure and strategic investments - Health focus: NHDIC subsidiary dedicated to healthcare - Political alignment: Government-to-government credibility - Beyond capital: Political protection, regulatory smoothing

Approach Strategy: 1. Request meeting through Minister of Science & Technology 2. Pitch as “National Genomics Infrastructure Investment” 3. Co-invest with IFC for credibility 4. Emphasize job creation and import substitution

Contact: NSIA Office of CEO, Healthcare Investment Team

### B. NHDIC (Nigeria Health Development & Investment Company): $5-20M (60% Probability)

Structure: NSIA subsidiary focused on healthcare

Relevant Programs: - Direct equity investment - MAMA Fund component management - World Bank co-investment vehicle

## 3.4 Strategic Investors (Pharmaceutical)

### A. Sanofi: $10-20M Equity + Partnership (60% Probability)

Example Structure:

| Component | Value | What Sanofi Gets |
| --- | --- | --- |
| Equity stake (15%) | $10M | Board observer, strategic alignment |
| SCD research partnership | $12M over 5 years | Exclusive 12-month data access |
| Total Value | $22M | 100K+ SCD patients, Nigerian market positioning |

### B. Other Pharma Strategic

| Company | Amount | Probability | Interest |
| --- | --- | --- | --- |
| Roche | $10-15M | 50% | Diagnostics platform |
| Illumina | $5-10M + equipment | 40% | Sequencing adoption |
| BGI | $5-10M + equipment | 40% | Technology partnership |

## 3.5 Impact Investors & Foundations

| Investor | Amount | Probability | Focus |
| --- | --- | --- | --- |
| Omidyar Network | $5-15M | 50% | Digital public goods |
| Skoll Foundation | $5-10M | 40% | Social enterprise |
| Mulago Foundation | $2-5M | 40% | Proven impact models |

## 3.6 Investment Staging Strategy

| Stage | Timing | Amount | Investors | Valuation |
| --- | --- | --- | --- | --- |
| Seed | Now | $500K-1M | Founders, angels | $3-5M pre |
| Series A | Month 12-18 | $5-10M | NSIA, impact | $15-25M pre |
| Series B | Month 24-36 | $15-25M | IFC, pharma strategic | $50-80M pre |
| Series C | Year 4-5 | $30-50M | Growth investors | $100-150M pre |

Valuation Drivers: - MeddyPal user base and revenue - Genomic database size (genomes sequenced) - Pharma partnership revenue - Government contract value - Comparable transactions (Flutterwave, 54gene)

# SECTION 4: PHARMACEUTICAL PARTNERSHIPS ($20-35M)

## 4.1 Why Pharma Pays Premium for Nigerian Data

- Population: 220M people = largest African market

- Sickle Cell: Nigeria has 150K+ births/year (highest globally)

- Genetic Diversity: African genomes have most novel variants

- Clinical Trials: Large patient populations for recruitment

- Regulatory Gateway: NAFDAC approval = pan-African market entry

The Data Value Gap: - Only 2% of genomic research includes African data - African-specific drug metabolism (e.g., 50% efavirenz toxicity on standard dose) - Novel disease variants not found in European databases - Pharma desperately needs African validation data

## 4.2 Target 1: Novartis - Sickle Cell Disease ($10-15M) - 75% Probability

Why Novartis: - Active Africa SCD Program in 6+ countries - Nigeria explicitly in CONSA (Consortium on Newborn Screening in Africa) - 60,000+ hydroxyurea treatments delivered in Ghana - 90,000+ babies registered in screening apps - Demonstrated commitment to African SCD

Our Offer:

"Exclusive Nigeria SCD Genomics Partnership"
Duration: 5 years
Novartis Investment: $12M ($2-3M/year)

What They Get:
Year 1-2:
- Access to 5,000 SCD patient genomes
- Linked clinical data through MeddyPal
- Genotype-phenotype correlation studies
- 12-month exclusive access before public release

Year 3-5:
- Access to 20,000 SCD patient genomes
- Longitudinal outcomes data
- Clinical trial recruitment infrastructure
- Joint publications (Novartis co-author)
- Priority licensing for diagnostics/therapeutics

What We Get:
- $12M funding over 5 years
- Technical support for SCD genomics
- Novartis brand credibility
- Pathway to clinical trials in Nigeria

Deal Structure:

| Phase | Timeline | Investment | Deliverables |
| --- | --- | --- | --- |
| Pilot | Year 1 | $2M | 1,000 SCD patients, validate linkage, 2-3 papers |
| Scale | Year 2-3 | $5M | 10,000 patients, 3 states, genetic modifiers |
| Sustain | Year 4-5 | $5M | Ongoing recruitment, real-world evidence, gene therapy prep |

Entry Point: - Racey Muchilwa, Country President, Novartis SSA - OR American Society of Hematology (ASH) CONSA partnership

Pitch Deck Elements: 1. Nigeria = largest SCD population globally (150K births/year) 2. Only 2% of SCD genetic research includes African data 3. Novartis drugs (hydroxyurea, gene therapy) need Nigerian validation 4. MeddyPal provides longitudinal outcomes data (unique!) 5. Government partnership = regulatory pathway for trials 6. Pathway to market for next-generation SCD therapies

Timeline: - Month 2-3: Initial outreach through ASH CONSA network - Month 4-5: Pitch deck and partnership proposal - Month 6-8: Negotiate terms and due diligence - Month 9-10: MOU signing - Month 12: First funding tranche ($2M pilot)

Risk Mitigation: - If Novartis declines → Pivot to Vertex Pharmaceuticals (new SCD gene therapy approved 2023) - Or Bluebird Bio (SCD gene therapy, seeking African validation)

## 4.3 Target 2: Roche Diagnostics - African Genomics Program ($8-12M) - 70% Probability

Why Roche: - 10-year Africa strategy: 10x diagnostic access by 2033 - African Genomics Program: “Open federation of biobanks hosted in Africa that are African-led” - Goal: Sequence >50,000 African genomes - Delivers 60% of all HIV viral load testing in SSA - Global Access Program: 50-70% equipment discounts for LMICs

Our Offer:

"Nigeria Node of Roche African Genomics Program"
Duration: 5 years
Roche Investment: $10M cash + $3M equipment = $13M total

What They Get:
- Access to 50,000 Nigerian genomes (African diversity)
- Validation data for Roche diagnostics in African populations
- Distribution network through MeddyPal
- Showcase for Roche Genomics Africa strategy
- Joint publications and conference presentations
- First access to Nigerian clinical trials

What We Get:
- $10M cash over 5 years ($2M/year)
- $3M equipment donation (sequencers, diagnostics)
- Roche technical support and training
- Global Access Program pricing (50-70% off)
- Roche brand credibility

Deal Structure:

| Phase | Timeline | Investment | Equipment | Deliverables |
| --- | --- | --- | --- | --- |
| Foundation | Year 1 | $2M | $1M (NAVIFY) | 5,000 genomes, MeddyPal integration, 2-3 papers |
| Scale | Year 2-3 | $4M | $2M (Cobas) | 25,000 genomes, validation studies, training |
| Sustain | Year 4-5 | $4M | - | 50,000 genomes, self-sustaining, clinical trials |

Equipment Donation Component: - NAVIFY oncology software platform - Cobas diagnostic systems (for pharmacogenomics) - AVENIO liquid biopsy kits - Total value: $3M over 5 years

Entry Point: - Bernard Colombo, President EMEA-LATAM, Roche Diagnostics International - OR Roche African Genomics Program team

Timeline: - Month 3-4: Initial contact through Roche Africa team - Month 5-6: Partnership proposal and deck - Month 7-9: Negotiate MOU and technical terms - Month 10-12: MOU signing and pilot initiation - Month 18: First major funding ($2M Year 1)

## 4.4 Target 3: Sanofi OR Novo Nordisk - Cardiometabolic ($8-12M) - 60% Probability

Rationale: Diabetes and cardiovascular disease = fastest growing health burden in Nigeria

Sanofi Offer: - $8-10M for Nigerian cardiometabolic genomics - Focus: Diabetes genetics, cardiovascular risk markers - Access to 30,000 patient genomic + metabolic data - Clinical trial recruitment for diabetes drugs

Novo Nordisk Offer: - $8-10M for diabetes genomics specifically - Focus: Type 2 diabetes genetics in African populations - GLP-1 response genetics - Obesity genetics

Decision: Approach both, negotiate with whoever responds first. Lock in by Month 18.

## 4.5 Standard Pharmaceutical Deal Structure (Template)

| Component | Standard Terms |
| --- | --- |
| Upfront Payment | $2-3M at signing |
| Milestones | $1M per 10,000 genomes enrolled |
| Annual Access Fee | $500K-1M for data access |
| Duration | 5 years with renewal option |
| Exclusivity | 12 months (then data becomes public) |
| Publications | Joint publications, pharma co-author |
| IP | Background IP retained, joint IP for discoveries |
| Revenue Share | NABDA 40% / Basani 60% |

## 4.6 Pharmaceutical Timeline & Sequencing

| Month | Action | Target Outcome |
| --- | --- | --- |
| 1-3 | Initial outreach to all 4 targets | Meetings scheduled |
| 4-6 | Pitch decks and proposals delivered | 2-3 in active negotiation |
| 7-9 | Negotiate terms, due diligence | 1-2 MOUs in draft |
| 10-12 | First MOU signed (Novartis priority) | $10-15M committed |
| 13-18 | Second MOU signed (Roche priority) | $18-27M committed |
| 19-24 | Third partnership initiated | $26-39M committed |

# SECTION 5: RESEARCH-FUNDED TESTING: GENOMICS-AS-A-SERVICE ($5-15M) ⭐ NEW

## 5.1 Core Concept

Research grants pay for individuals to receive FREE genetic testing through MeddyPal. Patients get free testing; we get platform users; researchers get data.

Research Funder (Gates, NIH, Pharma)
         │
         │ Pays $100-150 per test
         ▼
    MeddyPal Platform
         │
    ┌────┴────┐
    │         │
    ▼         ▼
Patient    Research
gets FREE  gets data
testing    (de-identified)
    │
    ▼
We Get:
• New lifetime user (LTV $50-100/year)
• Testing margin (20%)
• Insurance/telemedicine revenue
• Data for database

Why This Works: - Research funders WANT to pay for population testing - Free testing removes barrier to MeddyPal adoption - Each “free” test generates more value than paid test would - Builds database for pharma partnerships - Creates flywheel: more users → more data → more research → more free testing

## 5.2 Unit Economics

### Cost Structure

| Cost Component | Genotyping (Carrier) | WGS (Full Genome) |
| --- | --- | --- |
| Sample collection | $10-15 | $10-15 |
| Sequencing/genotyping | $30-50 | $200-400 |
| Bioinformatics | $10-20 | $50-100 |
| Result delivery | $5 | $10 |
| Genetic counseling | $10-20 | $20-50 |
| Total Cost | $70-120 | $300-595 |
| Price to Funder | $100-150 | $400-700 |
| Our Margin | $30 (20%) | $100-150 (15-25%) |

### The REAL Value Per “Free” Test

| Value Component | Amount | Notes |
| --- | --- | --- |
| Testing margin | $30 | Direct revenue from funder |
| New MeddyPal user LTV | $50-100/year | Insurance, telemedicine, bookings |
| Database value | $50-200 | For pharma partnerships |
| Insurance referral | $10-30 | One-time commission |
| Telemedicine revenue | $10-30/year | Ongoing engagement |
| Total Value per Patient | $150-360 | Over 3-5 years |

Key Insight: A “free” test generates $150-360 total value vs. $30 if we just charged patients directly.

## 5.3 Target Research Funding Programs

### A. Sickle Cell Disease (HIGHEST PRIORITY)

| Program | Funder | Potential Tests | Grant Value |
| --- | --- | --- | --- |
| SCD Grand Challenges | Gates Foundation | 50,000+ | $5-8M |
| SickleInAfrica Consortium | NIH/NHLBI | 10,000+ | $2-5M |
| CONSA Newborn Screening | ASH | 20,000+ | $3-5M |
| SCD Clinical Studies | Novartis | 5,000+ | Included in pharma deal |

Nigeria Opportunity: - 150,000+ SCD births/year (highest in world) - 25% carrier frequency (40M carriers) - Massive unmet need for screening - Funders actively seeking Nigeria programs

Example: Gates Foundation SCD Grant ($8M)

| Budget Component | Amount | Tests |
| --- | --- | --- |
| Carrier screening | $5M | 50,000 |
| Newborn screening | $1.5M | 10,000 |
| Platform development | $500K | - |
| Research/analysis | $500K | - |
| Program management | $500K | - |

MeddyPal Revenue from This Grant:

| Revenue Source | Calculation | Amount |
| --- | --- | --- |
| Testing margin (20%) | $6.5M × 20% | $1.3M |
| New users (60,000 × $50 LTV) | 60,000 × $50 | $3M (over 5 years) |
| Data value to pharma | Included in Novartis deal | $1.5M |
| Total Program Value |  | $5.8M |

### B. Pharmacogenomics Programs

| Program | Funder | Tests | Focus |
| --- | --- | --- | --- |
| GRADIENT | Novartis/GSK | 10,000+ | Drug metabolism |
| TB/HIV Optimization | Global Fund | 20,000+ | Treatment personalization |
| PEPFAR HIV Treatment | USAID | 50,000+ | Personalized ART |

Value Proposition: African patients have different drug metabolism. 50% efavirenz toxicity on standard dose. Testing optimizes treatment.

### C. Maternal/Child Health Programs

| Program | Funder | Tests | Integration |
| --- | --- | --- | --- |
| MAMA Fund | World Bank | 100,000+ | Carrier screening in antenatal care |
| Child Survival | Gates Foundation | 50,000+ | Newborn screening |
| Maternal Health | USAID/PEPFAR | 30,000+ | High-risk pregnancy screening |

Integration Model: Add carrier screening to antenatal care visits. Pregnant woman downloads MeddyPal for results. Becomes maternal health platform user.

### D. Disease-Specific Research

| Disease Area | Funder | Tests | Grant Value |
| --- | --- | --- | --- |
| Diabetes | Novo Nordisk | 20,000 | $2-4M |
| Cancer | Roche, AstraZeneca | 10,000 | $2-3M |
| Cardiovascular | Pfizer | 15,000 | $2-3M |
| Infectious Disease | Wellcome | 20,000 | $3-5M |

## 5.4 Patient Journey (MeddyPal Genomics)

1. AWARENESS
   └── Community health workers, radio, social media, clinic posters

2. ENROLLMENT
   └── Downloads MeddyPal app
   └── Creates account (now MeddyPal user!)
   └── Digital consent for testing and research
   └── Scheduled for sample collection

3. SAMPLE COLLECTION
   └── At NABDA center, partner clinic, or community outreach
   └── Blood or saliva sample
   └── Barcode linked to MeddyPal account

4. WAITING PERIOD (2-4 weeks)
   └── Engagement with MeddyPal features
   └── Educational content on genetics
   └── Insurance comparison (soft sell)
   └── Health profile completion

5. RESULTS DELIVERY
   └── Push notification when ready
   └── View results in app
   └── AI-powered plain language explanation
   └── Option for video genetic counseling

6. FOLLOW-UP
   └── Genetic counseling session (if needed)
   └── Partner testing recommendation (if carrier)
   └── Specialist referral (if condition found)
   └── Integration with primary care provider

7. LIFETIME ENGAGEMENT
   └── Regular health check-ins
   └── Insurance enrollment
   └── Telemedicine consultations
   └── Family member referrals
   └── Additional testing as needed

## 5.5 Revenue Projections

| Year | Tests Funded | Testing Revenue | New Users | Platform Revenue | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | 5,000 | $150K | 5,000 | $15K | $165K |
| 2 | 25,000 | $750K | 30,000 | $200K | $950K |
| 3 | 50,000 | $1.5M | 80,000 | $1.75M | $3.25M |
| 4 | 75,000 | $2.25M | 155,000 | $3.5M | $5.75M |
| 5 | 100,000 | $3M | 250,000+ | $5.25M | $8.25M |

5-Year Total: $18.4M revenue from research-funded testing program

## 5.6 The Flywheel Effect

More MeddyPal Users
       │
       ▼
More Health Data ──────────────────────────────────────┐
       │                                               │
       ▼                                               │
More Research Interest ◄───────────────────────────────┤
       │                                               │
       ▼                                               │
More Research Grants                                   │
       │                                               │
       ▼                                               │
More "Free" Testing ──► More MeddyPal Users ───────────┘
       │
       ▼
More Platform Revenue
       │
       ▼
More Sustainability

# SECTION 6: EQUIPMENT & CLOUD PARTNERSHIPS ($6-11M Value)

## 6.1 Why Equipment Partnerships are Critical

Standard vs. Donated Equipment Costs:

| Equipment | Market Price | With Partnership | Savings |
| --- | --- | --- | --- |
| NGS Sequencer (Illumina NovaSeq) | $1M | $400K (60% off) | $600K |
| NGS Sequencer (BGI DNBSEQ-G400) | $250K | Donated | $250K |
| Biobank freezers (-80°C) | $50K each | In-kind | $150K |
| Cloud infrastructure (5 years) | $5M | Credits | $4M |
| Total Potential Savings |  |  | $5M+ |

## 6.2 BGI/MGI Genomics - Equipment Donation ($2-3M Value) - 75% Probability

Why BGI: - Chinese government backing for Africa health partnerships - Established Africa operations (South Africa, Ethiopia) - 30-40% cheaper consumables than Illumina - Strong presence in genomics equipment donations globally

Our Offer to BGI:

"Nigeria Flagship Site for BGI Africa Genomics"

What We Offer BGI:
- Showcase installation in West Africa's largest country
- Published case study on government-private partnership
- West African training hub for BGI equipment
- 50,000+ genomes on BGI platform over 5 years
- Co-branded as "Powered by BGI"

What We Request:
- 1x DNBSEQ-G400 sequencer ($250K value)
- Installation and training (2 weeks, $50K value)
- 3-year consumables at cost ($300-400/genome)
- 3-year technical support ($100K value)
- Software licenses ($50K value)

Total Package Value: $2-3M

Entry Point: - Chinese Embassy in Nigeria (Science & Technology attaché) - BGI Africa office (Dr. Wilfred Njagi, Regional Director)

Pitch Elements: 1. Nigeria = largest African market (220M people) 2. Government partnership = stable, long-term customer 3. West African reference site (Anglophone Africa) 4. Scientific publications featuring BGI platform 5. Training hub creates customer pipeline

Timeline: - Month 1-2: Chinese Embassy introduction - Month 3: Formal proposal to BGI Africa - Month 4-6: Negotiation and site assessment - Month 6-9: Equipment delivery and installation - Month 9-12: Operational

## 6.3 Illumina Alternative - Subsidized Equipment ($800K-1.5M savings) - 60% Probability

If BGI Donation Falls Through:

| Program | Discount | Terms |
| --- | --- | --- |
| Illumina LMIC Program | 50-60% off | Developing country pricing |
| Illumina iHope Network | Equipment grants | Rare disease focus |
| Reagent Rental | Pay-per-sample | No upfront equipment cost |

Illumina Pricing (with LMIC discount):

| Equipment | List Price | LMIC Price | Savings |
| --- | --- | --- | --- |
| NextSeq 2000 | $335K | $140K | $195K |
| NovaSeq 6000 | $985K | $400K | $585K |
| MiSeq | $125K | $55K | $70K |

## 6.4 Cloud Infrastructure Partnerships ($3-6M Value)

### A. AWS Cloud Credits - $3-5M (70% Probability)

Programs:

| Program | Credits | Duration | Eligibility |
| --- | --- | --- | --- |
| Diagnostic Development Initiative | $3-5M | 5 years | Genomics + AI health |
| AWS Research Credits | $100K-500K | 1 year | Research institutions |
| AWS Activate | $100K | 2 years | Startups |

Our Pitch: - National genomics database (100K+ genomes) - AI for disease prediction (sickle cell, pharmacogenomics) - Government partnership (stable, long-term) - Case study for AWS health in Africa

Application Timeline: - Month 1: Submit through Diagnostic Development Initiative - Month 2-3: Review and decision - Expected: $1-3M approved initially, expandable to $5M

### B. Microsoft Azure - $2-3M (60% Probability)

Programs:

| Program | Value | Focus |
| --- | --- | --- |
| AI for Health | $2-3M cash + credits | Health AI research |
| Azure for Research | $1M credits | Academic partnerships |
| Nonprofit Credits | $500K | If structured as nonprofit component |

Our Pitch: MeddyPal AI for African health, genomic interpretation models

### C. Google Cloud - $1-2M (50% Probability)

Programs:

| Program | Value | Focus |
| --- | --- | --- |
| Google.org Impact Challenge | $2M cash + $1M credits | Health innovation |
| Research Credits | $500K | Academic |
| Cloud for Nonprofits | $350K | NGO component |

## 6.5 Equipment & Cloud Summary

| Partner | Value | Probability | Timeline | Status |
| --- | --- | --- | --- | --- |
| BGI Equipment | $2-3M | 75% | Month 6-9 | High priority |
| Illumina LMIC | $800K-1.5M | 60% | Month 3-6 | Backup |
| AWS Credits | $3-5M | 70% | Month 2-3 | Apply immediately |
| Azure Credits | $2-3M | 60% | Month 3-4 | Apply Month 3 |
| Google Credits | $1-2M | 50% | Month 4-6 | Lower priority |

Total Potential: $9-14.5M in equipment and cloud value

# SECTION 7: GOVERNMENT FUNDING ($11-20M)

## 7.1 The Government Funding Philosophy

Key Insight: Government funding is less about the money and more about political ownership. A government that funds a program will fight to sustain it.

| What Government Provides | Value |
| --- | --- |
| Political legitimacy | PRICELESS |
| Regulatory facilitation | PRICELESS |
| Inter-ministerial coordination | PRICELESS |
| Cash funding | Limited but growing |
| In-kind contributions | Significant |

Strategy: Start small, increase gradually. Build political commitment.

## 7.2 NABDA Direct Allocation - ₦8-15B over 5 years ($5-10M)

Current NABDA Budget Context: - NABDA total budget: ₦8-12B annually ($5.3-8M) - Personnel costs: ~60% (₦5-7B) - Available for programs: ₦3-5B ($2-3.3M)

Our Ask:

| Year | Amount | % of NABDA Budget | Purpose |
| --- | --- | --- | --- |
| 1 | ₦900M ($600K) | 7-10% | Pilot operations, staff |
| 2 | ₦1.5B ($1M) | 12-15% | Scale operations |
| 3 | ₦2B ($1.3M) | 15-18% | Full operations |
| 4 | ₦2.5B ($1.7M) | 18-20% | Sustainability |
| 5 | ₦3B ($2M) | 20-22% | Full funding |
| Total | ₦9.9B ($6.6M) |  |  |

Realistic Expectation: ₦5-8B over 5 years ($3.3-5.3M)

How to Secure: 1. Include in NABDA’s annual budget submission 2. Ministry of Science & Technology supplementary 3. National Assembly appropriation lobbying 4. Presidential intervention (if high profile)

## 7.3 Ministry of Science & Technology Supplementary - ₦3-5B ($2-3.5M)

Context: Minister has discretionary supplementary budget for priority initiatives

Our Ask: Position as flagship digital science initiative

| Year | Amount | Justification |
| --- | --- | --- |
| 1 | ₦500M ($330K) | Pilot and equipment |
| 2 | ₦800M ($530K) | Scale-up |
| 3 | ₦1B ($660K) | Operations |
| 4-5 | ₦1.5B ($1M) | Sustainability |

Strategy: - Personal meeting with Minister - Written “prayer” (formal request) - Tie to Ministry’s digital transformation agenda - Emphasize job creation and technology transfer

## 7.4 TETFund National Research Fund - ₦2-4B ($1.5-2.5M)

TETFund Context: ₦500B+ annual fund for tertiary education

Relevant Windows:

| Program | Amount | Focus |
| --- | --- | --- |
| National Research Fund | ₦1-2B per project | Research infrastructure |
| Institution-Based Research | ₦500M per institution | University genomics |
| Research Equipment | ₦500M-1B | Lab equipment |

Strategy: Partner with 3 universities for consortium application - University of Lagos (genomics) - Redeemer’s University (bioinformatics) - Ahmadu Bello University (Northern representation)

Timeline: Annual call typically Q3

## 7.5 PTDF Technology Transfer Fund - ₦500M-1B ($350-700K)

PTDF Context: Petroleum Technology Development Fund supports technology transfer

Our Angle: Genomics technology transfer, Nigerian capacity building

Realistic Expectation: ₦500M over 3 years

## 7.6 Presidential Special Allocation - ₦2-5B ($1.5-3.5M) - IF SECURED

Context: President has discretionary allocation for priority national projects

Triggers for Presidential Attention: - Major international recognition - Successful pilot with visible impact - Political value (diaspora engagement, international partnerships) - Health emergency response capability

Strategy: Do NOT pursue initially. Focus on operational success. Presidential allocation comes from visibility.

## 7.7 Government Funding Summary

| Source | 5-Year Target | Probability | Notes |
| --- | --- | --- | --- |
| NABDA Direct | ₦5-8B ($3.3-5.3M) | 70% | Annual budget inclusion |
| Ministry S&T | ₦2-3B ($1.3-2M) | 50% | Minister’s discretion |
| TETFund | ₦1.5-2.5B ($1-1.7M) | 60% | University partnership |
| PTDF | ₦500M ($330K) | 40% | Technology transfer |
| Presidential | ₦2-5B ($1.3-3.3M) | 30% | If high profile |
| Total Cash | ₦11-22B ($7.3-14.7M) |  |  |

In-Kind Contributions (Additional):

| Item | Value | Notes |
| --- | --- | --- |
| Office/lab space | ₦500M ($330K) | NABDA HQ |
| Staff assignment | ₦1.5B ($1M) | 10 NABDA staff |
| Equipment use | ₦500M ($330K) | Existing infrastructure |
| Regulatory support | PRICELESS | Fast-track approvals |
| Total In-Kind | ₦2.5B+ ($1.7M+) |  |

# SECTION 8: PLATFORM REVENUE - MEDDYPAL ($13-26M)

## 8.1 Why Platform Revenue is the Sustainability Key

The H3Africa Lesson: $180M in grants, zero commercial revenue → collapse when grants ended

Our Approach: MeddyPal generates revenue from Month 3, before any major grants disburse

| Metric | H3Africa | Our Model |
| --- | --- | --- |
| Time to first revenue | Never | Month 3 |
| % self-funded Year 5 | 0% | 40-50% |
| Platform users | 0 | 2M+ |
| Government dependency | 100% at end | <20% |

## 8.2 MeddyPal Revenue Streams (Detailed)

### A. Insurance Enrollment & Comparison - $2.5M (5 years)

Model: ₦500-1,000 ($0.35-0.70) per enrollment

| Year | Enrollments | Price | Revenue |
| --- | --- | --- | --- |
| 1 | 50,000 | ₦500 | ₦25M ($17.5K) |
| 2 | 200,000 | ₦750 | ₦150M ($105K) |
| 3 | 500,000 | ₦750 | ₦375M ($262K) |
| 4 | 1,000,000 | ₦1,000 | ₦1B ($700K) |
| 5 | 2,000,000 | ₦1,000 | ₦2B ($1.4M) |
| Total |  |  | ₦3.55B ($2.5M) |

Why Insurers Pay: Digital enrollment cheaper than agents (₦5,000 CAC), better data quality, access to genomic risk data

### B. Telemedicine & Appointments - $3M (5 years)

Model: ₦200-500 booking fee + premium subscription

| Year | Bookings | Fee | Subscription Revenue | Total |
| --- | --- | --- | --- | --- |
| 1 | 30,000 | ₦300 | - | ₦9M |
| 2 | 120,000 | ₦350 | - | ₦42M |
| 3 | 300,000 | ₦400 | ₦300M (10K subscribers) | ₦420M |
| 4 | 600,000 | ₦450 | ₦900M (25K subscribers) | ₦1.17B |
| 5 | 1,200,000 | ₦500 | ₦2.1B (50K subscribers) | ₦2.7B |
| Total |  |  |  | ₦4.34B ($3M) |

### C. Provider Operating System (SaaS) - $4.5M (5 years)

Model: Monthly subscription for hospitals and clinics

| Facility Type | Monthly Fee | Year 5 Target |
| --- | --- | --- |
| Large Hospital | ₦500K-2M | 20 facilities |
| Medium Clinic | ₦100K-200K | 80 facilities |
| Small Practice | ₦15K-50K | 100 facilities |

| Year | Facilities | Revenue |
| --- | --- | --- |
| 1 | 15 | ₦50M ($35K) |
| 2 | 35 | ₦180M ($126K) |
| 3 | 75 | ₦500M ($350K) |
| 4 | 130 | ₦900M ($630K) |
| 5 | 200 | ₦1.5B ($1.05M) |
| Total |  | ₦3.13B ($2.2M) |

### D. Laboratory & Pharmacy Integration - $770K (5 years)

Model: ₦300-800 per test/prescription facilitation

| Year | Lab Tests | Prescriptions | Revenue |
| --- | --- | --- | --- |
| 2 | 20,000 | 15,000 | ₦12.5M |
| 3 | 80,000 | 60,000 | ₦61M |
| 4 | 200,000 | 150,000 | ₦180M |
| 5 | 400,000 | 300,000 | ₦415M |
| Total |  |  | ₦669M ($468K) |

### E. B2B Analytics & Data Services - $1.5M (5 years)

Model: Data insights for insurers, researchers, pharma (de-identified)

| Year | Revenue | Clients |
| --- | --- | --- |
| 3 | ₦50M ($35K) | 3-5 |
| 4 | ₦100M ($70K) | 8-10 |
| 5 | ₦200M ($140K) | 15-20 |
| Total | ₦350M ($245K) |  |

Note: Separate from pharma partnerships (Section 4) - this is ad hoc analytics

### F. Premium Features & Subscriptions - $1.8M (5 years)

Model: ₦1,000-2,000/month for premium PHR features

| Year | Premium Users | Revenue |
| --- | --- | --- |
| 3 | 5,000 | ₦72M |
| 4 | 15,000 | ₦270M |
| 5 | 40,000 | ₦864M |
| Total |  | ₦1.2B ($840K) |

## 8.3 MeddyPal Total Revenue Projection (5 Years)

| Revenue Stream | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | 5-Year Total |
| --- | --- | --- | --- | --- | --- | --- |
| Insurance | ₦25M | ₦150M | ₦375M | ₦1B | ₦2B | ₦3.55B |
| Telemedicine | ₦9M | ₦42M | ₦420M | ₦1.17B | ₦2.7B | ₦4.34B |
| Provider SaaS | ₦50M | ₦180M | ₦500M | ₦900M | ₦1.5B | ₦3.13B |
| Lab/Pharmacy | - | ₦12.5M | ₦61M | ₦180M | ₦415M | ₦669M |
| B2B Analytics | - | - | ₦50M | ₦100M | ₦200M | ₦350M |
| Premium | - | - | ₦72M | ₦270M | ₦864M | ₦1.2B |
| TOTAL | ₦84M | ₦385M | ₦1.48B | ₦3.62B | ₦7.68B | ₦13.26B |
| USD | $59K | $269K | $1.04M | $2.53M | $5.38M | $9.3M |

Conservative Estimate: 60-70% of above = $5.6-6.5M over 5 years

## 8.4 MeddyPal Cost Structure

| Cost Category | Year 1 | Year 3 | Year 5 |
| --- | --- | --- | --- |
| Technology (hosting, dev) | ₦30M | ₦200M | ₦500M |
| Personnel | ₦25M | ₦150M | ₦350M |
| Marketing | ₦15M | ₦100M | ₦200M |
| Operations | ₦10M | ₦80M | ₦180M |
| Total Costs | ₦80M | ₦530M | ₦1.23B |
| Revenue | ₦84M | ₦1.48B | ₦7.68B |
| Margin | 5% | 64% | 84% |

# SECTION 9: GENOMIC SERVICES REVENUE ($5.5-11M)

## 9.1 Fee-for-Service Model (Year 2+)

Beyond research-funded testing, direct fee-for-service genomics generates revenue from: - Private patients (out-of-pocket) - Corporate wellness programs - Insurance-covered testing - Medical tourism

## 9.2 Service Menu & Pricing

| Service | Price (₦) | Cost (₦) | Margin | Target Volume Y5 |
| --- | --- | --- | --- | --- |
| Carrier Screening (SCD, thalassemia) | ₦35-50K | ₦25K | 40% | 20,000/year |
| Pharmacogenomics Panel | ₦50-80K | ₦35K | 40% | 15,000/year |
| Prenatal Screening (NIPT) | ₦150-200K | ₦100K | 35% | 5,000/year |
| Cancer Risk Panel | ₦200-300K | ₦150K | 30% | 3,000/year |
| Whole Genome Sequencing | ₦400-600K | ₦350K | 25% | 2,000/year |

## 9.3 Revenue Projections by Service

| Service | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| --- | --- | --- | --- | --- | --- |
| Carrier Screening | ₦100M | ₦250M | ₦500M | ₦800M | ₦1.65B |
| Pharmacogenomics | ₦50M | ₦150M | ₦350M | ₦600M | ₦1.15B |
| Prenatal (NIPT) | ₦30M | ₦100M | ₦250M | ₦500M | ₦880M |
| Cancer Risk | ₦20M | ₦60M | ₦150M | ₦300M | ₦530M |
| WGS Clinical | ₦40M | ₦120M | ₦280M | ₦500M | ₦940M |
| Total | ₦240M | ₦680M | ₦1.53B | ₦2.7B | ₦5.15B |
| USD | $168K | $476K | $1.07M | $1.89M | $3.6M |

## 9.4 Data Licensing Revenue

| Year | Revenue | Notes |
| --- | --- | --- |
| 3 | ₦100M ($70K) | First data licensing deals |
| 4 | ₦250M ($175K) | Multiple pharma partners |
| 5 | ₦500M ($350K) | Established data marketplace |
| Total | ₦850M ($595K) |  |

## 9.5 Genomic Services Total

| Category | 5-Year Total |
| --- | --- |
| Fee-for-Service | ₦5.15B ($3.6M) |
| Data Licensing | ₦850M ($595K) |
| TOTAL | ₦6B ($4.2M) |

# SECTION 10: COMPLETE COST BREAKDOWN

## 10.1 Capital Expenditures (CAPEX) - $11-17M over 5 years

| Category | Cost | Funding Source | Timing |
| --- | --- | --- | --- |
| Genomics Equipment |  |  |  |
| - Primary sequencer (BGI/Illumina) | $250K-1M | BGI donation or grant | Year 1 |
| - Backup sequencer | $200-400K | Grant | Year 2 |
| - Sample prep equipment | $150-250K | Grant | Year 1 |
| - Genotyping arrays | $100-200K | Grant | Year 1 |
| Subtotal Genomics | $700K-1.85M |  |  |
| Biobank Infrastructure |  |  |  |
| - -80°C freezers (10 units) | $500K | Grant + NABDA | Year 1-2 |
| - LN2 storage systems | $300K | Grant | Year 2 |
| - Automated storage | $400K | Grant | Year 3 |
| - Sample tracking system | $200K | Grant | Year 1 |
| Subtotal Biobank | $1.4M |  |  |
| IT Infrastructure |  |  |  |
| - Data center setup | $300-500K | Grant + NABDA | Year 1 |
| - Network infrastructure | $200K | Grant | Year 1 |
| - Security systems | $150K | Grant | Year 1 |
| Subtotal IT | $650K-850K |  |  |
| Cloud Credits | $3-5M | AWS/Azure | Year 1-5 |
| Lab Renovation | $500K-1M | NABDA + Grant | Year 1 |
| Office/Training Center | $300-500K | NABDA in-kind | Year 1-2 |
| TOTAL CAPEX | $6.55-10.6M |  |  |

With Donations/Credits: Effective cost $2-4M (60-70% in-kind)

## 10.2 Operating Expenditures (OPEX) - $45-70M over 5 years

### Personnel Costs

| Role | Year 1 FTEs | Year 5 FTEs | Year 5 Cost |
| --- | --- | --- | --- |
| Executive Leadership | 3 | 5 | ₦180M |
| Genomics Scientists | 5 | 20 | ₦400M |
| Bioinformaticians | 3 | 15 | ₦300M |
| Lab Technicians | 8 | 30 | ₦360M |
| IT/Data Engineers | 4 | 15 | ₦300M |
| Platform Developers | 6 | 20 | ₦400M |
| Operations/Admin | 5 | 20 | ₦240M |
| Genetic Counselors | 2 | 10 | ₦120M |
| Total Personnel | 36 | 135 | ₦2.3B ($1.6M) |

### Other Operating Costs

| Category | Year 1 | Year 3 | Year 5 | 5-Year Total |
| --- | --- | --- | --- | --- |
| Cloud/IT | ₦100M | ₦400M | ₦800M | ₦2.2B ($1.5M) |
| Lab Consumables | ₦200M | ₦600M | ₦1B | ₦3B ($2.1M) |
| Sequencing Reagents | ₦300M | ₦800M | ₦1.5B | ₦4.5B ($3.2M) |
| Sample Collection | ₦50M | ₦200M | ₦400M | ₦1B ($700K) |
| Quality/Compliance | ₦30M | ₦80M | ₦150M | ₦400M ($280K) |
| Marketing | ₦50M | ₦150M | ₦300M | ₦750M ($525K) |
| Admin/Overhead | ₦40M | ₦100M | ₦200M | ₦520M ($364K) |

### Total Operating Costs

| Year | Personnel | Other | Total |
| --- | --- | --- | --- |
| 1 | ₦400M | ₦770M | ₦1.17B ($820K) |
| 2 | ₦700M | ₦1.1B | ₦1.8B ($1.26M) |
| 3 | ₦1.2B | ₦2.3B | ₦3.5B ($2.45M) |
| 4 | ₦1.7B | ₦3.2B | ₦4.9B ($3.43M) |
| 5 | ₦2.3B | ₦4.15B | ₦6.45B ($4.52M) |
| Total | ₦6.3B | ₦11.55B | ₦17.85B ($12.5M) |

## 10.3 Total Program Costs Summary

| Period | CAPEX | OPEX | Total |
| --- | --- | --- | --- |
| Year 1-2 | $4-7M | $2.1M | $6.1-9.1M |
| Year 3-5 | $2-3.6M | $10.4M | $12.4-14M |
| 5-Year Total | $6-10.6M | $12.5M | $18.5-23M |

Note: With in-kind contributions and donations, effective cost is $12-17M

# SECTION 11: REVENUE SHARING FRAMEWORK

## 11.1 Intellectual Property Ownership

| IP Type | Owner | Commercial Rights |
| --- | --- | --- |
| MeddyPal Platform | Forric (100%) | Forric retains all rights |
| Existing NABDA Infrastructure | NABDA (100%) | Joint commercial use |
| Genomic Database | Joint (50/50) | Both parties consent required |
| AI/ML Models (new) | Developer (Basani) | NABDA gets public health license |
| Research Discoveries | Contributors | Co-filed patents possible |

## 11.2 Revenue Share by Source

| Revenue Source | NABDA | Basani | Rationale |
| --- | --- | --- | --- |
| MeddyPal Platform Revenue | 0% | 100% | Pre-existing Forric IP |
| Genomic Services (Year 1-5) | 30% | 70% | Basani takes operational risk |
| Genomic Services (Year 6+) | 40% | 60% | Mature partnership |
| Data Licensing | 50% | 50% | Equal contribution |
| Pharmaceutical Partnerships | 40% | 60% | Execution responsibility |
| Grant Funding | Activity-based | Activity-based | Depends on grant terms |
| Government Funding | NABDA controlled | Contracted | Standard government procurement |

## 11.3 If Syndicate Bio Joins

| Revenue Source | NABDA | Basani | Syndicate Bio |
| --- | --- | --- | --- |
| Genomic Services | 20% | 40% | 40% |
| Data Licensing | 33% | 33% | 34% |
| Pharmaceutical Partnerships | 25% | 40% | 35% |
| Platform Revenue | 0% | 100% | 0% |

# SECTION 12: SUSTAINABILITY ROADMAP

## 12.1 H3Africa vs. Our Model

| Factor | H3Africa (Failed) | Our Model |
| --- | --- | --- |
| Funding source | 100% grants | Mixed: grants + equity + revenue |
| Commercial revenue | Zero for 10 years | MeddyPal from Month 3 |
| Government ownership | Handover at end | Ownership from Day 1 |
| Exit plan | None | Break-even Year 3-4 |
| Pharma partnerships | Ad hoc, late | Structured from Year 1 |
| Platform/users | None | 2M+ by Year 5 |

## 12.2 Path to Self-Sustainability

| Year | Grant % | Platform % | Services % | Pharma % | Govt % | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 70% | 5% | 0% | 10% | 15% | Launch |
| 2 | 55% | 10% | 5% | 15% | 15% | Validation |
| 3 | 40% | 20% | 10% | 20% | 10% | Break-even |
| 4 | 30% | 30% | 15% | 15% | 10% | Profitable |
| 5 | 20% | 35% | 20% | 15% | 10% | Sustainable |

## 12.3 Break-Even Analysis

### Year 3-4 Target

| Item | Amount |
| --- | --- |
| Operating costs | ₦3.5-4.5B/year ($2.5-3M) |
| Platform revenue | ₦1.5B ($1M) |
| Genomic services | ₦700M ($490K) |
| Pharma partnerships | ₦1B ($700K) |
| Total Revenue | ₦3.2B ($2.2M) |
| Gap (covered by grants/govt) | ₦300M-1.3B |

### Year 5 Target

| Item | Amount |
| --- | --- |
| Operating costs | ₦6.5B/year ($4.5M) |
| Platform revenue | ₦7.7B ($5.4M) |
| Genomic services | ₦2.7B ($1.9M) |
| Pharma/data | ₦1.5B ($1M) |
| Total Revenue | ₦11.9B ($8.3M) |
| Surplus | ₦5.4B ($3.8M) |

## 12.4 Key Sustainability Metrics

| Metric | Year 1 | Year 3 | Year 5 | Target |
| --- | --- | --- | --- | --- |
| Grant Dependency | <80% | <50% | <30% | Declining |
| Platform Users | 50K | 500K | 2M | Growing |
| Revenue Growth | - | 200% YoY | 50% YoY | Positive |
| Operating Margin | Negative | 0% | 20-30% | Profitable |
| Genomes in Database | 1K | 25K | 100K | Growing |
| Staff Count | 36 | 85 | 135 | Growing |

# SECTION 13: IMPLEMENTATION TIMELINE

## 13.1 Months 1-3: Foundation

| Week | Actions | Funding Target |
| --- | --- | --- |
| 1-2 | MOA negotiation, team formation, infrastructure assessment | - |
| 3-4 | NABDA assessment complete, MeddyPal pilot prep, AWS application | AWS credits |
| 5-6 | Syndicate Bio negotiation, EDCTP3 pre-proposal | EDCTP3 pipeline |
| 7-8 | Gates concept note, legal completion | Gates pipeline |
| 9-10 | MOA signing, MeddyPal pilot launch | - |
| 11-12 | Genomics pathway confirmed, first pharma outreach | - |

Month 3 Target: $8-15M in pipeline, 5+ applications submitted

## 13.2 Months 4-12: Building Portfolio

| Month | Priority Actions | Expected Outcomes |
| --- | --- | --- |
| 4-6 | Pandemic Fund prep, pharma negotiations, IFC intro, BGI proposal | $15-25M pipeline |
| 7-9 | EDCTP Stage 2, Roche negotiation, NSIA meeting, TETFund | $25-40M pipeline |
| 10-12 | First pharma MOU signed, second pharma negotiating | $25-40M secured |

Month 12 Target: $25-40M secured, $40-60M pipeline

## 13.3 18-Month Funding Pipeline Visualization

MONTH 1-3: FOUNDATION
├── EDCTP3 Stage 1 pre-proposal → SUBMIT (€8-15M pipeline)
├── Gates Phase 1 exploratory → SUBMIT ($100K-500K)
├── Pandemic Fund concept note → DRAFT ($15-25M pipeline)
├── AWS cloud credits → SUBMIT ($3-5M)
├── Fleming Fund EOI → SUBMIT (£3-4M pipeline)
└── NSIA/AfDB engagement → MEETINGS

Expected by Month 3:
• AWS credits approved: $3-5M ✓
• 5+ applications submitted
• $15-25M in pipeline

MONTH 4-6: EXPANSION
├── EDCTP3 Stage 2 full proposal → IF INVITED
├── BGI equipment proposal → SUBMIT ($2-3M value)
├── Novartis partnership → NEGOTIATIONS
├── Roche partnership → PITCH
├── IFC introduction → MEETING
└── TETFund application → SUBMIT (₦1-2B)

Expected by Month 6:
• Fleming Fund approved: £3-4M ✓
• BGI equipment committed: $2M ✓
• Novartis MOU in draft: $10-15M
• $20-35M pipeline

MONTH 7-12: SCALE
├── EDCTP3 Stage 2 decision → SEPTEMBER
├── Novartis MOU signed → MONTH 10
├── Roche partnership → NEGOTIATIONS
├── JICA SATREPS application → NOVEMBER
├── Gates Phase 2 invitation → IF PHASE 1 SUCCESS
└── Pandemic Fund full proposal → PREPARE

Expected by Month 12:
• EDCTP3 approved: €8-12M ✓
• Novartis MOU signed: $10-15M ✓
• TETFund approved: ₦1-2B ✓
• $25-40M secured
• $40-60M pipeline

MONTH 13-18: CONSOLIDATION
├── Pandemic Fund decision → MARCH 2026 ($10-25M)
├── Roche MOU signed → MONTH 15 ($8-12M)
├── IFC due diligence → ONGOING
├── NSIA decision → MONTH 16 ($10-30M)
└── Second pharma partnership → MONTH 18

Expected by Month 18:
• $40-60M secured
• $60-80M total pipeline
• Platform generating $500K+/year revenue

## 13.4 Risk-Adjusted Funding Forecast

| Source | Target | Risk-Adjusted (70%) |
| --- | --- | --- |
| Pandemic Fund | $10-25M | $7-17.5M |
| EDCTP3 | €8-12M | €5.6-8.4M |
| Novartis | $10-15M | $7-10.5M |
| Roche | $8-12M | $5.6-8.4M |
| AWS Credits | $3-5M | $2.1-3.5M |
| BGI Equipment | $2-3M | $1.4-2.1M |
| Government | $3-5M | $2.1-3.5M |
| 18-Month Total | $52-92M | $30-53M |

# SECTION 14: RISK MANAGEMENT

## 14.1 Financial Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Major grant rejection | Medium | High | Diversified portfolio (10+ applications) |
| Platform revenue miss | Medium | Medium | Conservative projections, multiple streams |
| Pharma partnership fails | Medium | High | Multiple targets (4+), backup options |
| Government funding cut | Medium | Low | Minimize dependency (<15%) |
| Equity investment fails | Medium | Medium | Program viable without equity |
| Currency fluctuation | High | Medium | USD/Naira hedging, dollar contracts |
| Syndicate Bio partnership fails | Medium | Medium | NABDA build-out backup |

## 14.2 Operational Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| NABDA infrastructure non-functional | High | Medium | Contract sequencing backup |
| Key personnel departure | Medium | High | Competitive compensation, redundancy |
| Equipment failure | Low | High | Maintenance contracts, backup equipment |
| Data breach | Low | Very High | Security investment, insurance |
| Regulatory changes | Low | High | Government partnership buffer |

## 14.3 Mitigation Principles

- No single funding source >30% of total

- Multiple pathways for every critical need

- Commercial revenue from Day 1 (not dependent on grants)

- Conservative projections with upside scenarios

- Staged commitments based on milestone achievement

- Government partnership provides political buffer

# SECTION 15: IMMEDIATE ACTIONS

## 15.1 Week 1 Actions

### Basani Responsibilities

- ☐ Assign full-time grants manager (1 FTE)

- ☐ Engage Nigerian law firm for ICRC PPP

- ☐ Draft NSIA meeting request (through Minister)

- ☐ Submit AWS cloud credits application

- ☐ Contact BGI Africa office

### NABDA Responsibilities

- ☐ Assign 4 Task Team members by name

- ☐ Confirm Year 1 budget allocation commitment

- ☐ Prepare Ministry of Health introduction letter

- ☐ Schedule first Task Team meeting (Week 2)

- ☐ Complete infrastructure assessment (equipment status)

### Joint Actions

- ☐ Draft Gates Foundation concept note

- ☐ Begin EDCTP3 pre-proposal (due March 15)

- ☐ Schedule World Bank Nigeria office meeting

- ☐ Finalize MOA terms and timeline

## 15.2 Month 1-3 Milestones

| Milestone | Deadline | Owner | Status |
| --- | --- | --- | --- |
| MOA signed | Week 10 | Joint |  |
| MeddyPal pilot live | Week 10 | Basani |  |
| Gates concept note submitted | Month 2 | Basani |  |
| EDCTP3 pre-proposal submitted | March 15 | NABDA |  |
| Genomics pathway confirmed | Week 12 | Joint |  |
| AWS credits approved | Month 2 | Basani |  |
| NABDA infrastructure assessment | Week 4 | NABDA |  |
| First pharma contact made | Month 3 | Joint |  |

# CONCLUSION

## The Financial Model in One Page

Total 5-Year Target: $88-159M

| Source | Amount | Key Actions |
| --- | --- | --- |
| International Grants | $25-43M | 10+ applications, Pandemic Fund priority |
| Pharmaceutical Partners | $20-35M | Novartis, Roche, Sanofi partnerships |
| Platform Revenue | $13-26M | MeddyPal launch Month 3 |
| Equity Investment | $10-20M | SPV by Year 2, IFC/NSIA |
| Research-Funded Testing | $5-15M | Gates, CONSA, MAMA Fund |
| Genomic Services | $5.5-11M | Fee-for-service Year 2+ |
| Government | $11-20M | NABDA allocation, gradual increase |
| Equipment/Cloud | $6-11M | BGI, AWS, Azure donations |

## Sustainability Path

| Phase | Grant % | Revenue % | Status |
| --- | --- | --- | --- |
| Year 1-2 | 60% | 15% | Launch |
| Year 3-4 | 40% | 45% | Break-even |
| Year 5+ | 20% | 65% | Sustainable |

## Critical Differentiators from H3Africa

- Commercial revenue from Day 1 (MeddyPal platform)

- Research funding subsidizes user acquisition (free testing model)

- Equity structure enables long-term investment (SPV by Year 2)

- Government ownership from start (builds political commitment)

- Multiple pathways for every critical need (no single point of failure)

## The Bottom Line

This program achieves financial sustainability by Year 5, with or without continued grant funding. Every funding source builds toward self-sufficiency, not dependency.

The combination of platform revenue, research-funded testing, pharmaceutical partnerships, and gradual government contribution creates a resilient financial model that can survive the end of any single funding source.

Document Status: CONSOLIDATED MASTER DOCUMENT
Version: 2.0
Last Updated: December 2025
Next Review: After Month 3 results
Owners: Basani Digital Innovations + NABDA Joint Task Team